## Sheet1
Vendor | Item Description | Date Ordered | Date Shipped | Date Delivered | Status | PO Link | Comments | w/ TAMU Purchasing
COSMED | VO2 Mask | 2019-05-23 | n/a | n/a | w/ TAMU Purchasing | Link |  | w/ Vendor
Ideum | Touch Table | 2019-04-16 | n/a | n/a | w/ Vendor | Link |  | Shipped
Microsoft | Hololens 2 | n/a | n/a | n/a |  |  | Pending order, in talks with Microsoft | Received
miniSim | Driving Simulator | 2019-01-24 | n/a | n/a | w/ Vendor |  | Ouch. Targeting July delivery. TAMU sole source was a nightmare on this one
VICON | Desktop, software | 2019-05-22 | n/a | n/a | w/ TAMU Purchasing | Link
EEG Device
Note on E2: Tristan Griffith: The date you sent the PO to TAMU purchasing
Note on I2: Tristan Griffith: Make sure to include in the repo