## Sheet1
Vendor | Item Description | Date Ordered | Date Shipped | Date Delivered | Cost | Status | PO Link | Comments | w/ TAMU Purchasing
COSMED | VO2 Mask | 2019-05-23 | n/a | n/a | 42000 | Shipped | Link |  | w/ Vendor
Ideum | Touch Table | 2019-04-16 | n/a | n/a | 13000 | Shipped | Link |  | Shipped
Microsoft | Hololens 2 | n/a | n/a | n/a | 0 |  |  | Pending order, in talks with Microsoft | Received
miniSim | Driving Simulator | 2019-01-24 | n/a | n/a | 86000 | w/ Vendor |  | Ouch. Targeting July delivery. TAMU sole source was a nightmare on this one
VICON | Desktop, software | 2019-05-22 | n/a | n/a | 38000 | Received | Link
Enobio EEG Device | Clinical EEG device | 2019-05-29 | n/a | n/a | 22000 | w/ TAMU Purchasing | Link
Tobii Pro Glasses 2 | Eyetracking | 2019-05-06 | 2019-05-09 | 2019-05-12 | 30000 | Received | Link
empatica e4 | Wristband | 2019-01-28 | 2019-01-28 | 2019-01-28 | 3000 | Received | Link
BodyWave | Freer Logic | 2019-03-12 | 2019-03-12 | 2019-03-12 | 3300 | Received | Link
LooxidVR | VR w/ EEG | 2019-03-01 | 2019-03-01 | 2019-03-01 | 6000 | Received | Link
Custom Sensors | nanoPaint | 2019-04-12 |  |  | 5600 | w/ Vendor | Link | Still in development. They tested a number of substrates and will send us multiple units.
Hyrel Printer | 3D Printer | 2018-09-28 | 2018-09-28 | 2018-09-28 | 12000 | Received | Link
Teclab Benches | Benches | 2018-09-15 | 2018-09-15 | 2018-09-15 | 14000 | Received |  | Will add link when I get the document
Note on E2: Tristan Griffith: The date you sent the PO to TAMU purchasing
Note on J2: Tristan Griffith: Make sure to include in the repo